## Transition Project Plan
Project and Task Categories | Tasks and Considerations | Priority | Estimated Time (Days) To Complete | Est. Start Date | Est. Due Date | Notes
Hospital Linkage
Communication to Hospital Users | Notice of change
Educational Material
New Login URLs (if applicable)
New Logins (if applicable)
Changes in printed runform layout
Hospital / HIE access to records | Evaluate need for updates to APIs
Work with hospital or other HIE developers to update element and value mapping for data exchange integrations
Communicate needs for linkage updates that may be initiated on Service side- such as KNO2 or other
Patient Registries | Evaluate Data element changes for linkage or registry updates needed
Trauma
Cardiac Arrest
STEMI
Stroke
Other
Legal Updates
Data Use Agreements | Update NEMSIS DUA
Update DUAs with stakeholder partners as applicable
Software Contracts | Update any state contracts with your vendor if needed to change versions
Data Access | Update policies and processes for data requests and access
Laws | Update applicable state laws as needed
Reporting requirements
Dataset elements if required to be defined or referenced
Data Set | This is the defined list of data elements and values your state intends to collect
Gap Analysis and Plan | Compare V3.4 to V3.5 for requirements (done/provided by NEMSIS ahead of time?)
Download and review V3.5 NEMSIS Required elements
Conduct gap analysis for conflicts between datasets (done by NEMSIS ahead of time?)
Identify changes in element or value definitions needed for business rules and data dictionary
Identify V3.5 elements your State wants to collect from gap analysis
Custom Data Elements | Determine need for new V3.5 custom elements for state requirements
Define configuration for custom data elements or values
Value Lists | Review value lists for defined updates as needed
Cause of Injury
Provider Impression
Incident Location Type
Symptoms
Medications
Procedures
Review state value lists for vendors and NEMSIS dataset updates
Active EMS Agencies
Facilities
Approval Requirements | Publish Draft Data Set for review
Obtain approvals for updated data set with approving bodies as needed -examples: Data Advisory Council State EMS Approving Body / Commission / Board Medical Directors Stakeholder Groups or Hearings
Forward approved datasets to legal for law updates (if applicable)
Publish Data Set | Publish final approved State data set - (if applicable)
Compile dataset into state publishing format (i.e. excel sheet or merge document etc.)
Publish NEMSIS Dataset
Upload the following lists to NEMSIS V3.5 state data set builder: Custom Data Elements State Collected Elements State Certification/Licensure levels Procedures Permitted by State Medications Permitted by State EMS Agencies Facilities
New Data Set is now available for vendors to download from the NEMSIS site
Send dataset tables, references and breakout values, facilities etc. to NEMSIS for your state resource site if desired
Business Rules and Schematron
Point of Entry Business Rules | Use Element and Definition Gap Analysis to define POE requirements
Perform gap analysis between V3.4 POE rules and V3.5 requirements
Review NEMSIS Schematron for POE rules needed to meet National Rules
Build POE rules based on Gap analysis
ImageTrend states upload your validations to the library
State Schematron | Build V3.5 State Schematron (if applicable)
Use existing V3.4 State Schematron as a base
Update rules based off of updated V3.5 POE rules
Update rules directed to 3rd party imports outside of POE rules
Send updated Schematron to NEMSIS for validation and posting on the website once approved
Have your state's software vendor import the new Schematron into your system to make it live
ImageTrend states upload your Schematron to the library
Data Dictionary | This is a published compilation of your dataset, business rules, and other information such as state specific definitions and use case guides
Data Dictionary | Update State published Data Dictionary (If applicable)
Update page template as needed (such as if you want to display both V3.4 and V3.5 requirements)
Update sections and elements in the dictionary as needed
Update National and State requirements listing
| Update or insert new business rules into each element section | Get NH format for example
Update or insert new Schematron rules into each element section (if applicable)
Publish Final Data Dictionary to your state resources site
Send final copy to NEMSIS to have then add it to your state resources
State Software System Configuration | (Work with your software vendors various transition tools as available)
Data Element Manager | Use your published Dataset to configure your software's dataset manager
Configure (activate / inactivate) all V3.5 elements in your state system
Configure any value changes identified in each element
Run Form | Create an updated run entry form with V3.5 element changes
Create updated Printout configuration as needed
Point-Of-Entry Business rules | Sometimes called validation rules
Configure update in your system for POE rules based off of prepared updates
System integrations | Work with your software vendor to update any software configurations as previously identified in preparation
State Built software | Work with your state software programmers to incorporate all prepared work and updates
Timelines will be heavily dependent on the programming updates
Plan for software testing internally and with pilot agencies
System Transition Plan
Timeline | Establish time needed for preparation of all above items
Determine when you software vendor will have the software ready and approved by NEMSIS for use
Determine training needs for services to make the transition
Determine amount of time to prepare the training material
Determine amount of training time needed for services to use updated software
Identify amount of time to pilot new software and make fixes
Determine amount of lead time 3rd party vendors will be allowed to transition -This may be influenced by when the 3rd party software will be NEMSIS approved
Determine amount of time needed to approve 3rd party software at the state level for use (if applicable)
Establish final timeline based on all the above determinations then add at least 30-60 days to find your transition date
Service Communications | Publish Transition timeline
Create emails, letters, newsletters, pamphlets, promo videos or other communications to your Service Admins
Establish stakeholder meetings to present updates and provide training plans
Encourage service leaders to work with their billing vendors to prepare for transition -Many billers have software they can import run records into, which also needs to be updated to receive the records
Education | Create / update written guides for service leaders or providers as desired
Update any training videos or other training resources for both service administrators and providers
Train internal state staff as necessary
Data Query system | Update any data query systems, tables or reports to extract V3.5 data as needed
Establish any cross-walk references or tables needed to translate changes as needed
Update data access guides for service admins as applicable
Elite (Software Vendor) 3rd Party Vendors
Communications | Contact all 3rd party vendors to provide transition deadline
Importing Software Approval | Update software approval process as needed
Update dataset requirements for 3rd party vendors
Update compatibility approval guides as needed
3rd Party Software Approval | Have all vendors complete any updated approval process in preparation for transition
NH Data Dictionary Format
Dataset comparison table
Schematron Comparison table